## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact the SSC Program Advisor, Micah Kenfield, at kenfield@illinois.edu
GENERAL INFORMATION
Project Title: | Student Space Systems - Liquid Rocket Engine
Total Amount Requested from SSC: | 20000
Amount Requested as: | GRANT | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Complete design of liquid engine prototype (LEP) injector plate | 4 |  | 2016-04-28
Complete design of LEP igniter module | 4 |  | 2016-04-28
Submit LEP design files to GPI Prototypes for DMLS manufacturing | 5 |  | 2016-05-05
Receive completed components from GPI | ~ |  | Depends on GPI - ideally the last week of June
Purchase fuel and oxidizer pumps /hoses for LPE | 12 |  | 2016-06-10
Purchase fuel and oxidizer once LPE components are received from GPI | 14 |  | 2016-06-22
Assemble and test LPE | 15 |  | 2016-06-30
Complete design of liquid engine two (LE2) | 35 |  | 2016-11-17
Submit LE2 design files to GPI for DMLS manufacturing | 37 |  | 2016-12-02
Receive completed LE2 components from GPI | ~ |  | Depends on GPI - ideally the first week of February
Assemble and test LE2 | 47-49 |  | 2017-03-04
Certify LE2 for flight readiness | 51 |  | 2017-03-17
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
LPE thrust chamber | 7216.58 | 1 | 7216.58
LPE injection plate | 677.93 | 1 | 677.93
LPE igniter module | 1049.44 | 1 | 1049.44
LPE pumps/hoses/regulators | 2000 | 1 | 2000
Fuel and oxidizer for testing | 1000 | 1 | 1000
LE2 projected cost | 12000 | 1 | 12000
0
0
0
|  | Subtotal | 23943.95
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
|  | TOTAL BUDGET | 23943.95
ENVIRONMENTAL AND ECONOMIC IMPACTS
Please include any other sources of funding that have been obtained or applied for, and please attach any relevant letters of support.
Please estimate the greenhouse gas impact this project will have, if applicable. Use the University of Illinois at Urbana-Champaign Energy Management website to determine the cost of energy on campus and the following chart to determine GHG emissions.
| Electricity: 1.672 CO2lb/kWh | Diesel: 22.2 CO2lb/gallon
| Steam: 244.9 CO2lb/klb | Gasoline: 19.4 CO2lb/gallon
Chilled Water: 144.6 CO2lb/mmbtu
Our only sources of greenhouse gas is the electricity that our computational and design computers use estimated to be 300 CO2lb in the next year and the CO2 in the exhaust estimated to be 2.58 CO2lb per ten second firing of the LPE and 5.41 CO2lb per ten second firing of the LE2.
End of Application