## Sheet1
Funding Application: Student RFP
Please complete this application and any supporting documentation by 11:59pm, March 12, 2014 and email it to Marika Nell at nell2@illinois.edu. Use the subject line "SSC Student RFP: [Project Title]." Please be sure to spell check your application and correct any errors before submission. The committee will assess the application and may request additional documentation that will be due before January 31, 2014. Funding decisions will be made on February 15, 2014 and funding will be made available in March. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact the SSC Chair Marika Nell at nell2@illinois.edu.
GENERAL INFORMATION
Project Title: | SECS Re_Home Landscaping Project
Total Amount Requested from SSC: | 4008
Amount Requested as: | GRANT | (LOAN or GRANT) | Topic Areas
Please select the topic area(s) that best describes your project: | Land |  | Energy | Land
|  |  | Food & Waste | Education
|  |  | Water | Transportation
CONTACT INFORMATION
Applicant/Project Leader
Name: | Brandon Giannoni
Student Group or Department: | Students for Environmental Concerns (SECS)
Email: | bgianno2@illinois.edu
Phone Number: | 773-414-5359
Organization Code (for CFOP): | 1758
Faculty Sponsor/Financial Contact
Name: | Dr. Xinlei Wang
Role: | Site Owner
Faculty/Unit/Department: | Department of Agricultural and Biological Engineering
Email: | xwang2@illinois.edu
Phone Number: | 217-819-4742
Project Team: | Name |  | Organization/Department | Email
| Dr. Xinlei Wang |  | Dept. of Ag. and Bio. Engineering | xwang2@illinois.edu
| Kevin Donovan |  | Architecture | kevin.p.donovan@gmail.com
| Brandon Giannoni |  | SECS | bgianno2@illinois.edu
| Leah Wurster |  | SECS | lwurste2@illinois.edu
PROJECT DESCRIPTION
Provide a brief background of the project, the goals, and desired outcome.
The Re_Home, developed by students and faculty here at the University of Illinois to compete in the 2011 Solar Decathlon, will now be permanantly located on campus and for this reason, a landscaping and beautification plan is currently under development. In maintaining "sustainability ideology", the landscaping plans for this project are geared toward sustainability with the use of native, low maintenance plants as well as vegetables, edible herbs, and fruit trees. The Re_Home is an exemplary embodiment of sustainability and acts as a showcase in sustainability education with target audiences not only including students of the University of Illinois and of education centers within the Urbana-Champaign region, but students and tourists at a national and even global scale as well.
Describe how the project will improve the sustainability of the Illinois campus and how the project goes above and beyond campus standards.
Within this particular landscaping project, current plans and objectives are set in order to augment the "sustainability ideology" that the Re_Home exemplifies. I doing so, native, low-maintenance plants (currently Butterfly weed, sky-blue aster, and little bluestem), an edible garden (beans, basil, lettuce, sage, oregano, rosemary), and a fruit tree (drought-tolerant Prairiefire crabapple) are all included. Incorporating such plants has the potential to increase local diversity of invertabrates essential to the pollination process including numerous butterfly and bee species -which are currently declining in many areas due to habitat loss and pesticide application. Carbon sequestration and soil organic carbon assimilation will also be augmented by native plants and fruit trees within the project via the long, branching root systems and carbon-rich woody material formed by such species. Upkeep of these native, low-maintenance species is of very little concern once these plants are established, reducing the need for supplemental irrigation as well. Implementing an edible garden will increase awareness regarding the use of organic, locally-grown food, which eliminates the need for pesticide and herbicide application and greatly reduces the carbon footprint that such store bought food would entail because of tranasportation.
Where will the project be located? Will special permissions be required to enact the project on this site? If so, please explain and attach any letters of support at the end of the application.
The project will take place at 3603 South Race Street, Urbana IL which is the current permanent location of the Re_Home. Permission has already been granted to carry out this project by the site owner, Dr. Wang.
Other than the project team, who will have a stake in the project? Please list other individuals, groups, or departments affiliated directly or indirectly by the project. This includes any entity providing funding (immediate, future, ongoing, matching, in-kind, etc.) and any entities that will be benefitting from this project. Please attach letters of commitment or support at the end of the application.
The Department of Agricultural and Biological Engineering here at UIUC will have a stake in the project due to the fact that the Re_Home itself is affiliated with the department through Dr. Wang and the Solar Decathlon program. Local nurseries contacted during this project for advice and/or material will also have a stake in this project. Prospective nurseries currently include Prairie Gardens, Country Arbors, and Allerton Park.
Please indicate how this project will involve or impact students. What role will students play in the project?
Our student group (SECS) is looking to play a large role in the completion of this project, which will be done via the implementation of work days. During these designated work days, students will actively prepare and manage various portions of the landscaping plan for the Re_Home. Our main duty will be to create and upkeep the edible garden located at the house, which includes various herbs and vegetables within planters as well as a vertical garden.
Have you applied for funding from SSC before? If so, for what project?
I have not applied for SSC funding before. However, both SECS and the Solar Decathlon program have applied for SSC funding seperately in the past.
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Meet with local nurseries to discuss plans | 2 |  | 2014-03-21
Obtain materials and supplies | 2 (excluding Spring Break week) |  | 2014-04-11
Obtain plants, landscaper installation of native plants and tree, SECS works on edible garden (weather dependent) | 4 |  | 2014-05-09
Request project be placed on SECS website | 1 |  | 2014-05-16
Place garden signs at home | 1 |  | 2014-05-23
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Shovels | 30 | 2 | 60
Trowels | 8 | 3 | 24
Hand Cultivator | 20 | 1 | 20
Pruner | 15 | 1 | 15
Watering Can | 8 | 1 | 8
Bucket | 5 | 1 | 5
Trellis | 15 | 2 | 30
Rain Barrel | 140 | 1 | 140
Composting Unit | 80 | 1 | 80
0
|  | Subtotal | 382
Publicity & Communication
Garden Signs | 27 | 5 | 135
0
0
0
0
0
0
0
0
0
|  | Subtotal | 135
Personnel & Wages
Approximately 800 sqare feet professional landscaping: native plants and fruit tree | 3 | 800 | 2400
0
0
0
0
0
0
0
0
0
|  | Subtotal | 2400
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
Prairiefire Crabapple, 2" Base | 200 | 1 | 200
Butterfly Weed | 8 | 15 | 120
Sky Blue Aster | 8 | 15 | 120
Little Bluestem | 8 | 25 | 200
Herbs | 12 | 9 | 108
Bean and Lettuce Seeds | 3 | 6 | 18
Soil | 5 | 25 | 125
Student Transportation | 200 | 1 | 200
0
0
|  | Subtotal | 1091
|  | TOTAL BUDGET | 4008
If the project is implemented, will there be any ongoing funding required? What is the strategy for supporting the project in order to cover replacement, operation, or renewal costs? (Note: SSC provides funding on a case by case basis and should not be considered as an ongoing source of funding)
No, ongoing funding for this project is not an issue, for most species of plants chosen are hardy perennials that require little maintanence once established. Only a small portion of the plants utilized (annual vegetables) will need to be replaced year after year as the Re_Home managers see fit. Ongoing maintanence of the Re_Home and its components (including landscaping) will be carried out by those affiliated with the Re_Home and the Department of Agricultural and Biological Engineering.
Please include any other sources of funding that have been obtained or applied for, and please attach any relevant letters of support.
Applied for: Scotts Miracle-Gro Company GRO1000 Grassroots Grant
ENVIRONMENTAL, SOCIAL, AND ECONOMIC IMPACTS
In this section, please describe the impact this project will have on this campus. Which aspects of sustainability will the project address? Does the project fit within one of the iCAP goals? If so, please describe. Does the project go above and beyond current university standards and policies? Please describe.
At present, the ideal that is sustainability has far reaching effects and is particularly relevant and noticeable at a community level. The Re_Home exemplifies this ideal, linking environmental, economic, and social sustainability to create a very efficient tool by which sustainability education and demonstration can be achieved. With aligning landscaping themes to correlate with the aforementioned goals, the effectiveness of demonstrating "sustainability ideology" will be greatly heightened. With this in mind, the University of Illinois will continue its trajectory toward becoming a more environmentally-friendly and conscious community by working toward the iCAP goals that the University has agreed to enforce.
Please include any other sources of funding that have been obtained or applied for, and please attach any relevant letters of support.
Applied for: Scotts Miracle-Gro Company GRO1000 Grassroots Grant
EDUCATION, OUTREACH, AND PUBLICITY PLAN
Please note that all projects are required to publicize SSC's financial contribution by whatever means are most appropriate for the project. Photo documentation of the project's progress and completed product are required in addition to the interim and final reports. Note that your project may be selected to present a poster at a symposium. The SSC Program Advisor will work with the project team in conjunction with Illini Union Marketing to determine what is best suited for the project.
What is the plan for publicizing the project on campus? In addition to SSC, where will information about this project get reported?
Subsequent to the completion of this project, SECS will update its website to include the general project outcome and acknowledge all groups/organizations/companies that assisted in the completion of the Re_Home landscaping. The project will also likely be mentioned during numerous general meeting days and during Quad Day the following fall semester as a marketing and public outreach tool. We also plan on having garden signs made to be placed at the Re_Home to be viewed by any potential visitors/tourists, one of which will acknowledge any and all groups involved in the landscaping project.
Please list specific outreach goals and ways in which the outreach can be measured.
In carrying out such a landscaping and beautification project, greater emphasis is placed on "showing off" the Re_Home and extolling the University's commitment to sustainability. Publicizing the Re_Home itself as an exemplary embodyment of sustainability and sustainability education and amplifying the University's goals regarding environmental awareness are important facets of this landscaping project. The Re_Home is not only open to the student body and potential tourists at a local level, but to those at a national and even global level as well. Such visitation can be utilized as a baseline by which to measure success of outreach objectives.